## Sheet1
| Task | Start Date | End Date | Duration | User Stories
Sprint 0 | Data Modeling | 2024-09-27 | 2024-10-11 | 14
Sprint 1 | Account Creation/Profile Page | 2024-10-11 | 2024-10-25 | 14 | As a user, I want to create an account, so that I can access my financial tracking information.
Sprint 2 | Landing Page/Income & Expense Page | 2024-10-25 | 2024-11-08 | 14 | As a user, I want to add my income and expenses, so that I can track my monthly and yearly financial activities
Sprint 3 | Feature Implementation and Testing | 2024-11-08 | 2024-11-29 | 21 | As a user, I want to categorize my income and expenses, so that I can understand where I am earning/spending money
Sprint 4 | Project Documentation and Delivery Presentation | 2024-11-29 | 2024-12-13 | 14
Statement of Proposal: We propose to create a personal financial web application that
will allow users to track their monthly and yearly income and expenses. The application will be
able to categorize income and expenses and provide users with an overview of their current
financial situation based on the monthly data entered. The application will allow users to create
an account that stores their income/expenses and graphical data to allow for easy access from
any device